## Kế hoạch triển khai
PROMPTIFY → INTREPID · TECHNICAL IMPLEMENTATION PLAN
Deadline | 2026-10-23 | Tiến độ | 0% | P0 chưa xong | 54 | Blocker | 0
Feature Freeze: 20/10 · Rehearsal: 21–22/10 · Pilot: 23/10
Reuse React/Vite/Supabase/Vercel. 3–5 task/ngày; i18n foundation P0 từ 07/10, EN mặc định + VI; locale/content/AI language tách biệt. Giải pháp là đề xuất, chưa implement.
Sheet mẫu Dương tạo; manual Sync. Chỉ ghi blocker đã xác minh; credential GCP/SOP thiếu quyền cần kiểm ngày 08/13. Sau pilot: Redis/auto-sync/SSE, analytics/library nâng cao, ingestion/video, multi-tenant/white-label/payment/partner/clone.
Ngày | Mốc | Technical Task | Code / DB bị tác động | Ưu tiên | Owner | Kết quả cần đạt | Trạng thái | Blocker / Ghi chú
2026-10-06 | M1 — Identity | [Reuse] Kiểm branch/env và tách pilot deploy/DB | vercel.json / vite.config.ts / supabaseClient.ts | P0 | Dương | Pilot chạy React/Vite/Supabase riêng; xác định ledger 016/017. | Đang làm
2026-10-06 | M1 — Identity | [Modify] Map resolveUserSession và OAuth identity | App.tsx / dbService.ts / users, learners | P0 | Dương | Xác định đường auto-create hiện tại và mapping auth UID → user. | Đang làm
2026-10-06 | M1 — Identity | [DB] Thiết kế delta roster, membership và Head | schema.sql / types/database.ts; migration mới | P0 | Dương | Chọn membership 1 department/user cho pilot; country và Head role rõ. | Chưa làm
2026-10-07 | M1 — Identity | [DB] Thêm department/country và roster snapshot | supabase/migrations (mới) / types/database.ts | P0 | Dương | DB pilot có roster/membership; email normalized unique, role không lấy từ Sheet. | Chưa làm
2026-10-07 | M1 — Identity | [Modify] Gate Intrepid identity phía server | App.tsx / apiAuthorizationService.ts | P0 | Dương | JWT hợp lệ và email đã xác thực; domain ngoài allowlist bị từ chối. | Chưa làm
2026-10-07 | M1 — Identity | [DB] Siết auth UID link và quyền đổi role | dbService.ts / RLS users, learners | P0 | Dương | Auth UID unique; learner không sửa role/department hoặc tự link user khác. | Chưa làm
2026-10-07 | M1 — Identity | [New] Thiết lập i18n EN-default, VI và fallback EN | src/i18n + locales/en,vi (mới) / main.tsx / package.json | P0 | Dương | EN mặc định; switch VI và nhớ lựa chọn. Thiếu key/locale fallback EN; thêm locale bằng resource. | Chưa làm | Foundation nhẹ (đề xuất i18next/react-i18next); code mới dùng t(key), không hard-code UI text.
2026-10-08 | M1 — Identity | [RLS] Thêm department scope cho class/content | RLS classes/enrollments/courses; migration mới | P0 | Dương | Seed 2 department kiểm được quyền; Head không dùng is_instructor global. | Chưa làm
2026-10-08 | M1 — Identity | [Modify] Bỏ public enroll và non-UUID bypass | App.tsx / apiAuthorizationService.ts | P0 | Dương | Intrepid không self-enroll; API bắt buộc lesson UUID thuộc course được phép. | Chưa làm
2026-10-08 | M1 — Identity | [Test] Login/role isolation và credential smoke | LandingLoginScreen.tsx / apiServerService.ts | P0 | Dương | OAuth refresh/logout đúng; role không tự tăng; generate/Judge credential chạy thật. | Chưa làm
2026-10-09 | M2 — Sheet + Profile | [New] Tạo Sheet demo 4 field, 2 department | Google Sheet mẫu (ngoài codebase) | P0 | Dương | 10 user có Email/Full Name/Department/Country; Dương cấp backend quyền đọc. | Chưa làm
2026-10-09 | M2 — Sheet + Profile | [New] Đọc private Sheet phía backend | api/roster-sync.ts + sheetRosterService.ts (mới) | P0 | Dương | Server đọc được Sheet/tab cấu hình; secret không vào frontend. | Chưa làm
2026-10-09 | M2 — Sheet + Profile | [New] Parse và validate roster theo row | sheetRosterService.ts (mới) | P0 | Dương | Trim/lower email; thiếu field, duplicate và department lạ báo row lỗi. | Chưa làm
2026-10-10 | M2 — Sheet + Profile | [DB] Upsert roster/learner/enrollment idempotent | RPC import_roster (mới) / users, learners, enrollments | P0 | Dương | 10 row vào DB; import lại không trùng; batch lỗi không apply nửa chừng. | Chưa làm
2026-10-10 | M2 — Sheet + Profile | [New] Nối manual Sync roster cho Trainer | InstructorViewShell.tsx / api/roster-sync.ts (mới) | P0 | Dương | Chỉ Trainer sync được; UI thấy success/error và row lỗi. | Chưa làm
2026-10-10 | M2 — Sheet + Profile | [Test] Lỗi Sheet/import giữ snapshot thành công | sheetRosterService.ts / RPC import_roster (mới) | P0 | Dương | Timeout/duplicate/bad row không xóa roster hoặc progress cũ. | Chưa làm
2026-10-10 | M2 — Sheet + Profile | [Modify] Tách UI locale, content locale, AI output language | types/database.ts / curriculumAdapter.ts / llmService.ts / AI API | P1 | Dương | Ba giá trị độc lập; đổi UI không đổi course/context/AI language. AI language được validate phía server. | Chưa làm | Giữ content gốc, không dịch toàn bộ lesson. Dùng locale code ổn định; không dùng nhãn dịch làm business ID.
2026-10-11 | M2 — Sheet + Profile | [Modify] Match roster sau OAuth, bỏ auto-resolve cũ | App.tsx resolveUserSession / dbService.ts | P0 | Dương | Email đã xác thực match roster; ngoài roster không vào learning zone. | Chưa làm
2026-10-11 | M2 — Sheet + Profile | [New] Thêm confirm profile và correction state | App.tsx / ProfileConfirm.tsx (mới) / membership | P0 | Dương | Learner xác nhận 4 field; yêu cầu sửa không tự tăng quyền. | Chưa làm
2026-10-11 | M2 — Sheet + Profile | [Modify] Route zone từ membership/enrollment | App.tsx / dbService.ts / classes, enrollments | P0 | Dương | Learner mở đúng class/department; direct URL không đổi scope. | Chưa làm
2026-10-11 | M2 — Sheet + Profile | [Modify] Tách strings auth/profile/zone thành keys | LandingLoginScreen.tsx / App.tsx / ProfileConfirm.tsx (mới) | P1 | Dương | Auth/profile/zone chính và thông báo lỗi có EN/VI keys; switch locale không đổi identity/quyền. | Chưa làm
2026-10-12 | M2 — Sheet + Profile | [RLS] Siết lesson/resources/attempt/progress đọc | RLS lessons/resources/prompt_attempts/lesson_progress | P0 | Dương | Learner/Head A không query dữ liệu B; Trainer dùng assignment được cấp. | Chưa làm
2026-10-12 | M2 — Sheet + Profile | [Test] Negative JWT/roster/department requests | apiAuthorizationService.ts / API + Supabase tests | P0 | Dương | No JWT, ngoài roster, lesson sai course và department khác đều bị chặn. | Chưa làm
2026-10-12 | M2 — Sheet + Profile | [Test] Sheet → DB → login → confirm → zone | App.tsx / api/roster-sync.ts / membership | P0 | Dương | 10 user mẫu chạy thật; sửa Sheet rồi manual sync đổi scope đúng. | Chưa làm
2026-10-13 | M3 — Learning flow | Chọn SOP/sample data được phép dùng cho pilot | Nội dung lesson_resources / lessons | P0 | Thầy Đức | Có 1 scenario Intrepid, SOP và sample data được duyệt gửi AI. | Chưa làm
2026-10-13 | M3 — Learning flow | Chốt lesson/rubric và feedback nghiệp vụ | lessons / lesson_rubric_criteria (nội dung) | P0 | Thầy Đức | Một lesson có mục tiêu/rubric rõ; không tự áp threshold mastery. | Chưa làm
2026-10-13 | M3 — Learning flow | [Reuse] Seed course/module/lesson thật, bỏ fallback | CourseCurriculumEditor.tsx / App.tsx / curriculumAdapter.ts | P0 | Dương | Course published gắn department; lỗi DB không dùng LABS_DATA làm bài thật. | Chưa làm
2026-10-14 | M3 — Learning flow | [Modify] Generate resolve SOP/context server-side | api/generate.ts / apiServerService.ts / lesson query | P0 | Dương | Server tải lesson_resources canonical; không tin inputContext client. | Chưa làm
2026-10-14 | M3 — Learning flow | [Modify] Judge dùng rubric/output canonical | api/evaluate.ts / aiEvaluationContract.ts | P0 | Dương | Evaluate dùng lesson rubric và output server lưu theo run ID. | Chưa làm
2026-10-14 | M3 — Learning flow | [Reuse] Adapt AI provider theo credential thực tế | apiServerService.ts / llmService.ts / vite.config.ts | P0 | Dương | Generate/Judge dùng credential Intrepid; dev/Vercel cùng contract, không key browser. | Chưa làm
2026-10-15 | M3 — Learning flow | [DB/API] Lưu run/attempt bằng kết quả server | api/generate.ts / api/evaluate.ts / RPC mới | P0 | Dương | Run ID gắn user/lesson; client không tự ghi output/score được tin cậy. | Chưa làm
2026-10-15 | M3 — Learning flow | [DB] Sửa validator NULL và siết RPC provenance | migrations 016/017 + migration mới / prompt_attempts | P0 | Dương | JSON thiếu key không có best_score; forged write bị chặn; trigger progress atomic. | Chưa làm
2026-10-15 | M3 — Learning flow | [Modify] Hybrid dùng run ID và save/error state | HybridView.tsx / llmService.ts / dbService.ts | P0 | Dương | Output/Judge/save khớp run; save fail không báo completed; retry không trùng. | Chưa làm
2026-10-16 | M3 — Learning flow | [Reuse] Reload attempts và compare 2 lần chạy | HybridView.tsx / PromptComposer.tsx / dbService.ts | P0 | Dương | Rerun/compare từ attempt thật; refresh/login lại giữ progress. | Chưa làm
2026-10-16 | M3 — Learning flow | [Test] Evaluate retry/save failure và run overlap | HybridView.tsx / RPC attempts, lesson_progress | P0 | Dương | Retry Judge không thêm attempt; run cũ không ghi đè output mới. | Chưa làm
2026-10-16 | M3 — Learning flow | Nghiệm thu learning slice trên dữ liệu Intrepid | App.tsx / HybridView.tsx / curriculum DB | P0 | Dương + Thầy Đức | Lesson → AI → feedback → rerun/compare → refresh chạy đúng nghiệp vụ. | Chưa làm
2026-10-16 | M3 — Learning flow | [Modify] Tách strings lesson/playground thành keys | HybridView.tsx / PromptComposer.tsx / LessonBriefPanel.tsx | P1 | Dương | Nhãn lesson/run/feedback/rerun/compare/progress có EN/VI; SOP/sample giữ content locale. | Chưa làm
2026-10-17 | M4 — Trainer + Head | [Modify] Trainer query theo course assignment | InstructorViewShell.tsx / dbService.ts / course_instructors | P0 | Dương | Trainer đọc đúng learner/cohort/course được giao; bỏ client global aggregation. | Chưa làm
2026-10-17 | M4 — Trainer + Head | [Reuse] Gắn SOP/sample bằng text/URL resources | CourseCurriculumEditor.tsx / lesson_resources | P0 | Dương | Trainer sửa SOP/sample và reload còn dữ liệu; không xây ingestion mới. | Chưa làm
2026-10-17 | M4 — Trainer + Head | [Modify] Publish/assign lesson cho department | CourseCurriculumEditor.tsx / courses, classes | P0 | Dương | Draft không hiện cho learner; published assigned lesson tải đúng context. | Chưa làm
2026-10-18 | M4 — Trainer + Head | [Modify] Route Head vào view read-only | App.tsx / InstructorViewShell.tsx / role mapping | P0 | Dương | Head không mở CRUD/Sync của Trainer; login vào đúng department. | Chưa làm
2026-10-18 | M4 — Trainer + Head | [RLS] Chặn Head đọc/sửa ngoài department | RLS users/classes/enrollments/progress | P0 | Dương | Head A chỉ SELECT scope A; direct request sửa hoặc đọc B bị từ chối. | Chưa làm
2026-10-18 | M4 — Trainer + Head | [Reuse] Query progress tối thiểu cho Head | dbService.ts / InstructorViewShell.tsx / lesson_progress | P0 | Dương | Head thấy learner, attempts và last activity; completed run không gọi mastery. | Chưa làm
2026-10-19 | M4 — Trainer + Head | [Modify] Save lesson/rubric/resources nhất quán | CourseCurriculumEditor.tsx / dbService.ts / RPC mới | P0 | Dương | Save lỗi không để lesson nửa cập nhật; publish sau đủ content. | Chưa làm
2026-10-19 | M4 — Trainer + Head | [Modify] Tách cache/session theo account-class | App.tsx / HybridView.tsx / localStorage keys | P0 | Dương | Logout/login account khác không thấy prompt/output/assistance cũ. | Chưa làm
2026-10-19 | M4 — Trainer + Head | [Modify] Tách Trainer/Head UI strings thành keys; ẩn key controls | InstructorViewShell.tsx / CourseCurriculumEditor.tsx / PromptComposer.tsx | P1 | Dương | Trainer/Head và curriculum editor có EN/VI keys; learner không nhập/xem secret API key. | Chưa làm
2026-10-19 | M4 — Trainer + Head | [Test] Kiểm EN/VI fallback và locale independence | src/i18n (mới) / App.tsx / AI API / Trainer, Head UI | P1 | Dương | Missing key fallback EN; refresh giữ UI locale. EN UI + VI content/AI chạy độc lập; không lỗi quyền/layout. | Chưa làm
2026-10-20 | M4 — Trainer + Head | [Deploy] Đồng bộ migration/API/UI lên pilot | vercel.json / vite.config.ts / migrations mới | P0 | Dương | Pilot deploy đúng revision/schema; smoke auth/import/AI/progress thành công. | Chưa làm
2026-10-20 | M4 — Trainer + Head | [Test] Regression Trainer/Head/publish trên pilot | InstructorViewShell.tsx / RLS / curriculum editor | P0 | Dương | CRUD/publish và progress 2 department đúng scope trên DB deployed. | Chưa làm
2026-10-20 | M4 — Trainer + Head | Nghiệm thu 3 vai trò và đóng băng feature | App.tsx / HybridView.tsx / InstructorViewShell.tsx | P0 | Dương + Thầy Đức | Learner/Trainer/Head dùng được; sau 20/10 chỉ sửa lỗi chặn pilot. | Chưa làm
2026-10-21 | M5 — Hardening | [Test] E2E Sheet → learning → progress reload | Browser pilot / roster API / AI API / DB | P0 | Dương | Chạy toàn flow bằng user thật; ghi lỗi/repro vào Ghi chú task. | Chưa làm
2026-10-21 | M5 — Hardening | [Test] JWT/RLS và cross-department/role matrix | apiAuthorizationService.ts / RLS pilot DB | P0 | Dương | Learner/Trainer/Head và direct requests không vượt scope. | Chưa làm
2026-10-21 | M5 — Hardening | [Test] Roster/AI/save lỗi và login/logout | Sheet service / HybridView.tsx / RPC / App.tsx | P0 | Dương | Malformed roster, provider fail, save fail và refresh không mất/lộ dữ liệu. | Chưa làm
2026-10-22 | M5 — Hardening | [Fix] Sửa lỗi chặn pilot theo repro ngày 21 | Module/API/RLS có lỗi; xác định từ rehearsal | P0 | Dương | Lỗi P0 được sửa và test lại; không mở scope feature. | Chưa làm
2026-10-22 | M5 — Hardening | [Test] Chạy regression và rehearsal lần 2 | Browser pilot / AI API / Supabase RPC/RLS | P0 | Dương | Các case lỗi PASS lại; toàn flow chạy 2 lần không duplicate attempt. | Chưa làm
2026-10-22 | M5 — Hardening | [Deploy] Chốt release và kiểm cấu hình rollback | Vercel config / Supabase migration ledger | P0 | Dương | Release/schema tương thích; biết cách quay UI/API về bản ổn không mất data. | Chưa làm
2026-10-23 | M5 — Hardening | [Test] Final smoke pilot URL và credential | Pilot deploy / auth / roster / generate/evaluate | P0 | Dương | Import/login/AI/save hoạt động; không feature development lớn. | Chưa làm
2026-10-23 | M5 — Hardening | Nghiệm thu pilot end-to-end ba vai trò | App.tsx / HybridView.tsx / InstructorViewShell.tsx | P0 | Dương + Thầy Đức | Đức xác nhận flow nghiệp vụ và progress đúng department. | Chưa làm
2026-10-23 | M5 — Hardening | [Fix] Xử lý blocker pilot và retest scope bị ảnh hưởng | Module/API/RLS phát sinh lỗi khi pilot | P0 | Dương | Nếu có blocker: sửa/retest; nếu không: kiểm stability, không thêm feature. | Chưa làm

## UI
Complete UI Inventory Table for Promptify (Intrepid MVP)
#ID | UI Name | UI Purpose | Primary User | Secondary User | When to Use | Belong to Which User Story | Note (Design Specs, M3 Components & Technical Guidance)
UI-00 | Public Landing Page & Conversion Portal (/) | Introduce Promptify's core value proposition ("Output is the Destination, Prompting is the Means"), showcase the interactive "Try → Revise → Compare → Understand" Learning Loop via an embedded mini-demo, present the BASIC (Free) vs. ADVANCE (Paid) syllabus & pricing tiers, capture individual B2C signups, and collect B2B enterprise demo leads. | Prospective Individual Learner (B2C) | Enterprise L&D Admin / B2B Client PIC | First touchpoint when an unauthenticated public visitor accesses the root URL (https://promptify.ai/). | US-BRD2-01: As a prospective learner or enterprise L&D manager, I want to explore Promptify's learning philosophy, preview an interactive prompt comparison, and view pricing plans so I can sign up for a Free account or request a B2B demo. | M3 Spec: Top App Bar with Navigation Links (Features, Syllabus, Enterprise, Pricing) and an embedded UI-01 Auth CTA button. Hero section with Expressive Typography, Live Mini-Playground Widget (toggle between unguided vs. grounded AI output), Syllabus breakdown, B2B Client Logo Wall (Agribank, Intrepid Asia), Pricing Tier Cards (Basic Free vs. Advance Paid), and two primary CTAs: "Start Free with Google" (triggers embedded UI-01) and "Book Enterprise Demo" (opens B2B Lead Modal).
UI-01 | Google Workspace SSO & Auth View / Component (/auth/login or embedded in UI-00) | Authenticate users via Google OAuth, enforcing the @intrepid.asia or registered enterprise client domain boundary, handling initial language/locale selection (EN/VI), and routing verified users to Profile Confirmation (UI-02) or Learner Dashboard (UI-04). | Learner (Intrepid Staff / Business User) | Enterprise Training Lead / System Admin | Functions as an embedded component inside UI-00 for public SaaS onboarding, and as a standalone dedicated screen on /auth/login for enterprise subdomains (intrepid.promptify.ai) or session expiration redirects. | US-M1-01: As an Intrepid or enterprise employee, I want to log in using my company Google account so my identity and department are securely verified. | M3 Spec: Rendered as an embedded M3 Auth Box in UI-00 or a standalone Surface Container High card on /auth/login. Features Google OAuth trigger, real-time domain validation feedback, Language Selector dropdown (EN default / VI fallback), and automatic error handling for unauthorized domains (redirects to UI-03). Milestone: M1.
UI-02 | Profile Confirmation & Department Routing View (/onboarding/profile-confirm) | Display auto-matched roster metadata (Employee ID, Manager, Dept) and allow users to confirm or request department correction before entering the playground. | Learner (Intrepid Staff) | Enterprise Training Lead | Immediately after first successful SSO login before accessing Codelabs. | US-M2-02: As a learner, I want to verify my assigned department and employee details so I am routed to my correct Department Training Zone. | M3 Spec: Modal Bottom Sheet / Elevated Card layout (ProfileConfirm.tsx). Reads from roster-sync RPC; includes a "Confirm & Proceed" primary CTA and "Report Mismatch" secondary CTA. Milestone: M2.
UI-03 | Access Denied & Domain Guard View (/auth/access-denied) | Block non-Intrepid users or unregistered emails and provide clear instructions to contact the Enterprise Training Lead. | Unauthenticated / External User | System Admin | Triggered automatically when an OAuth attempt originates outside @intrepid.asia or email is absent from the Roster. | US-M1-02: As a System Admin, I want to block non-Intrepid email domains so enterprise context and SOP data remain secure. | M3 Spec: Full-screen M3 Alert State (Error Container color role) with icon, explicit reason description, and a "Switch Account" CTA button. Milestone: M1.
UI-04 | Learner Department Training Hub (/learner/dashboard) | Serve as the home landing view for learners, displaying their assigned department banner, Codelab progress (Labs 1–5), and SOP context resources. | Learner (Intrepid Staff) | Enterprise Training Lead | After logging in and confirming profile; used to launch or resume training labs. | US-M3-01: As a learner, I want a clear view of my 5-lab learning path and department SOPs so I can track my masterclass completion. | M3 Spec: Navigation Rail layout (Desktop) / Navigation Bar (Mobile). M3 Outlined Cards for Codelabs 1–5 with Linear Progress Indicators, Status Badges (Not Started, In Progress, Completed), and Dept SOP Badges. Milestone: M3.
UI-05 | Interactive Dual-Pane Codelab Workspace (/learner/playground/:labId) | Main execution playground providing a dual-pane environment to read scenario context, compose prompts (with {{variable}} support), and view real-time LLM outputs. | Learner (Intrepid Staff) | Enterprise Training Lead / Trainer | Used during active practice sessions to write, test, and refine prompts against real Gemini models. | US-M3-02: As a learner, I want a dual-pane workspace to write prompts against department SOP scenarios so I can see live AI outputs side-by-side. | M3 Spec: M3 Split-Screen Container. Left Pane: Task Scenario, Control Data, SOP Drawer. Right Pane: Prompt Composer (monospaced text area, variable tokens), Execute CTA (Gemini 3.8 Flash), Run History list. Milestone: M3.
UI-06 | Side-by-Side Prompt & Output Diff Viewer (/learner/playground/compare) | Visually compare two execution attempts (Prompt V1/Output V1 vs. Prompt V2/Output V2) side-by-side to highlight exact structural and output changes. | Learner (Intrepid Staff) | Trainer / Workshop Lead | Used after running at least 2 prompt attempts to analyze version progression during the "Compare" stage of the Learning Loop. | US-M3-03: As a learner, I want to compare my previous and current prompt outputs side-by-side so I can visually verify improvements in tone and formatting. | M3 Spec: M3 Two-Column Layout (DiffViewer.tsx) with visual syntax highlighting (green additions, red deletions) and a "Restore Version" action button. Milestone: M3.
UI-07 | AI Judge Diagnostic Scorecard & Drawer (/components/AIJudgeScorecard) | Present an automated 5-criteria evaluation breakdown (0–2 pts each, Total 10), diagnostic strengths/weaknesses, and a nextHint for prompt improvement. | Learner (Intrepid Staff) | Trainer / Enterprise Training Lead | Rendered automatically after prompt execution via server-side evaluation (Gemini 3.8 Pro). | US-M3-04: As a learner, I want automated diagnostic scores across 5 criteria so I know exactly how to improve my prompt on the next attempt. | M3 Spec: M3 Side Sheet / Expandable Card. Shows 5 Segmented Linear Gauges (Task Completion, Groundedness, Format, Constraints, Usability), numeric score badge (0–10), and an explicit "Retry Evaluation" CTA button if async timeout occurs. Milestone: M3.
UI-08 | SOP Context & Audit Inspector Drawer (/components/SOPContextDrawer) | Display department-specific SOP documents, brand guidelines, or ticket logs with exact page/section citations for zero-hallucination validation. | Learner (Intrepid Staff) | Trainer / Dept Head | Opened via the left pane in Codelab 1 (Zero-hallucination SOP Audit) or Codelab 5 (Grounding). | US-M3-05: As a learner, I want to inspect original department SOP documents alongside my prompt so I can cite exact page numbers and eliminate hallucinations. | M3 Spec: M3 End Side Sheet (SOPContextDrawer.tsx) with PDF/Markdown text renderer, search highlight filter, and "Copy Citation Tag" CTA. Milestone: M3.
UI-09 | Real-Time Workshop Command Center (/trainer/dashboard) | Provide trainers with a live overview of cohort health, "stuck" learners, 5-technique completion heatmaps, and real-time activity telemetry. | Enterprise Training Lead (Võ Từ Đức) / Trainer | System Admin | Used by trainers throughout live 100-minute masterclass workshops to monitor 1,150 employees across cohorts. | US-M4-01: As a Trainer, I want a 5-second clarity dashboard showing stuck learners and real-time execution streams so I can intervene immediately. | M3 Spec: Executive Command Center. Top: "Featured Attention Class Card" (Primary Container glow). Center: 5-Technique Progress Matrix. Bottom: Live Telemetry Event Stream (Run ID, Attempt Count, Score). Milestone: M4.
UI-10 | Learner Detail Modal & Prompt Inspector (/trainer/inspect/:learnerId) | Allow trainers to inspect a specific student's verbatim prompt syntax, attempt history, diagnostic scores, and issue a 1-click learning reminder. | Enterprise Training Lead / Trainer | Department Head | Opened when clicking on a stuck learner or low-scoring entry in the Trainer Command Center. | US-M4-02: As a Trainer, I want to inspect a student's exact prompt submission and send a reminder so I can guide them when they run too many failed attempts. | M3 Spec: M3 Dialog / Full-Screen Surface Container (PromptInspector.tsx). Shows verbatim prompt code block, 5-lab checklist, attempt counter, and a "Send Nudge" Toast button. Milestone: M4.
UI-11 | Curriculum & SOP Mapping Studio (/trainer/curriculum) | Enable the Enterprise Training Lead to map Intrepid's ~550 SOPs and sample data context into the 5 Codelabs and 27 Department Training Zones. | Enterprise Training Lead | Department Head | Pre-workshop setup or when updating training materials for specific departments. | US-M4-03: As the Enterprise Training Lead, I want to map company SOPs to specific department zones so learners practice on relevant work tasks. | M3 Spec: M3 Master-Detail View. Left: 27 Department selector. Right: Codelab 1–5 slot mapper with drag-and-drop file attach for lesson_resources. Milestone: M4.
UI-12 | Department Executive Progress Dashboard (/dept-head/dashboard) | Read-only analytics portal for Department Heads to track team-level completion, average AI Judge scores, and AI adoption metrics across business functions. | Department Head | Enterprise Training Lead | Used weekly or post-workshop by managers to review department workforce AI readiness. | US-M4-04: As a Department Head, I want a read-only progress report of my team's completion rates so I can evaluate AI adoption in my department. | M3 Spec: M3 Data Table & Metric Cards (DeptHeadDashboard.tsx). Enforced via RLS (user_metadata.department_id); includes CSV export for L&D reporting. Milestone: M4.
UI-13 | Department SOP Upload & Context Modal (/dept-head/sops) | Allow Department Heads to submit new SOP documents, campaign templates, or customer support logs for ingestion into their department's Codelab context. | Department Head | Enterprise Training Lead | Used whenever department workflows update or new SOPs need to be added to the training library. | US-M4-05: As a Department Head, I want to upload new department SOPs so the training platform reflects our latest operational standards. | M3 Spec: M3 Modal Dialog with File Drag-and-Drop, document metadata tagger (Department, Version, Confidentiality Level), and Upload Status Snackbar. Milestone: M4.
UI-14 | System Governance & API Key Monitor (/admin/governance) | Monitor centralized GCP API Key consumption, enforce rate limits (20 req/min), session token caps (50k/session), and monitor server-side LLM errors. | System Admin | Enterprise Training Lead | Continuous backend health monitoring, particularly during high-concurrency live workshops. | US-M5-01: As a System Admin, I want to monitor API Key quotas and error rates so the platform remains stable and cost-controlled during workshops. | M3 Spec: M3 Admin Dashboard. Real-time Gauge charts for Rate Limit quota, Token Usage progress bar, error log table, and "Emergency Throttle" toggle. Milestone: M5.
UI-15 | Google Sheets Roster Sync Management View (/admin/roster-sync) | Inspect 5-minute background Service Account sync logs, view imported learner counts, and manually trigger sync with Intrepid's private Google Sheet. | System Admin | Enterprise Training Lead | Used during onboarding setup, roster updates, or troubleshooting unlisted learner emails. | US-M2-01: As a System Admin, I want to trigger and monitor Google Sheets roster syncs so new employee data is automatically updated in Supabase. | M3 Spec: M3 Data Table rendering roster_sync_logs (sync_id, status, synced_users_count, timestamp). Includes a "Manual Sync Now" Primary Button with loading state. Milestone: M2.
Key Architectural & Design Highlights (Material 3 & System Alignment)
Strict Tri-Language Separation:
UI Locale: Rendered using M3 localized strings (English default, Vietnamese fallback).
Content Locale: Codelab scenarios and Intrepid SOPs maintain their native operational language (e.g., English for regional E-commerce ops, Vietnamese for local banking/customer support).
AI Output Language: Evaluated independently by the AI Judge based on prompt instructions.
Server-Side AI Gateway Security:
All LLM execution calls (UI-05, UI-07) are routed strictly through server-side API endpoints (/api/generate and /api/evaluate) using backend GCP API keys. No API keys are exposed to the client browser.
Multi-Tenant Data Isolation (RLS):
Department Heads (UI-12) and Learners (UI-04) are restricted strictly to their assigned department_id via Supabase Row-Level Security policies, ensuring confidential SOPs stay within their respective department zones.
This UI specification provides a complete reference for frontend engineering (Vite/Next.js + Tailwind M3) and product alignment leading up to the October 23, 2026 Pilot Launch.